## Sheet1
S.No | Activity | Check List Items | Description
2 | Scope Definition | List of Assets to Test | Domains / Subdomains (e.g., www.example.com, api.example.com)
IP Addresses or Ranges (e.g., 192.168.1.0/24) Total Number of Rest API's : Total Number of SOAP API's :
Internal Networks (for internal VAPT) Number of internal IP's (Count): Number of external IP's (Count): List of Assests with IP address critial order: Reachability - VPN (internal) : Scan Window ( For Scanning Inside environment): External Testing - whitelisting of IP in relevant firewalls , IPS / IDS devices for performing VA: Antiviurs disable in server ( Timelien of Scan window) :
Mobile Apps (APK, IPA, test credentials)
Web Applications / APIs (URLs, endpoints, Swagger docs)
Cloud Assets (AWS, Azure resources, etc.)
|  | Excluded Assets | Clear list of systems that must not be tested (due to sensitivity, availability concerns, etc.)
3 | Testing Environment Details | Staging vs Production Environment | Will testing be done in staging, UAT, or production?
Any change freeze or deployment schedule during testing?
|  | Maintenance Window / Testing Timeframe | Preferred testing hours to minimize downtime risk (esp. for production)
Duration of testing (e.g., 5 days, 2 weeks)
|  | Access Requirements | VPN / Bastion host access for internal scans
Whitelisting of your IPs (if applicable)
Test credentials (for authenticated scans – web apps, APIs, internal systems)
4 | Technical Contacts and Escalation Matrix | Point(s) of Contact | Name, email, phone of technical contact during testing
24x7 contact for critical alerts or system outage
|  | Incident Response Plan | Instructions on what to do if a system goes down or a critical vulnerability is discovered
5 | Compliance and Reporting Requirements | Compliance Requirements (if any) | PCI-DSS, ISO 27001, HIPAA, etc.?
Any specific controls or checks to include?
|  | Reporting Preferences | Report format (PDF, Excel, JSON, etc.)
Separate technical and executive summary reports?
CVSS scoring required?
6 | Legal & Liability Clarifications | Liability Clarification | Client understands the risk of DoS, system crash, or data loss (esp. for production scans)
Any insurance coverage or risk mitigation clauses?
|  | Permission to Store or Analyze Data | Explicit permission to handle sensitive data during assessment (temporarily or otherwise)
7 | Tool & Technique Limitations | Client-Approved Tools (if restricted) | Any tools or scanners not allowed?
Are automated scans permitted?
|  | Test Type Agreement | Black-box, Grey-box, or White-box testing?
Social engineering, phishing, or physical testing included?
8 | Other Documents | Architecture Diagram or Network Topology
Previous VAPT Reports (for benchmarking or regression testing)
API Documentation (Postman collection, Swagger, etc.)
List of Third-Party Services / Vendors Integrated